## Sheet1
Development | Assigned to | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
|  | 2/17 - 2/23 | 2/24 - 3/2 | 3/3 - 3/9 | 3/10 - 3/16 | 3/17 - 3/23 | 3/24 - 3/30 | 3/31 - 4/6 | 4/7 - 4/13 | 4/14 - 4/20 | 4/21 - 4/27 | 4/28 - 5/4 | 5/5 - 5/11
Phase 1
SRS Document |  | Week 7: 3/6 (Thursday)
- 1. Purpose | Talhah | bar: Week 5 to Week 7
- 2. Overall Description | Zoheb | bar: Week 5 to Week 7
- 3. Specific Requirments | Zoheb | bar: Week 5 to Week 7
- 4. Non-Functional Requirments | Sean | bar: Week 5 to Week 7
- 5. Use Cases | Zoheb | bar: Week 5 to Week 7
- 6. UML Class Diagrams | Kenny | bar: Week 5 to Week 7
- 7. UML Sequence Diagrams | Kenny | bar: Week 5 to Week 7
Gantt Chart | Sean | bar: Week 5 to Week 7
Project Presentation Slides | Talhah | bar: Week 5 to Week 7
Project Presentation |  | Week 7: 3/6 (Thursday)
Phase 2
Design Document |  | Week 12: 4/10 (Thursday)
1. Use Case Diagram/ Cases | Zoheb | bar: Week 6 to Week 9
2. Updated Class Diagram | Kenny | bar: Week 8 to Week 12
3. Classes Descriptions | Talhah | bar: Week 8 to Week 12
4. Sequence Diagrams | bar: Week 6 to Week 12
a. IT Admin Diagrams | Kenny | bar: Week 8 to Week 12
b. GUI and Client Diagrams | Zoheb | bar: Week 8 to Week 12
5. Prototype | bar: Week 8 to Week 12
a. Paper Prototype | Talhah | bar: Week 8 to Week 12
b. Mockup Prototype | Talhah/Zoheb | bar: Week 8 to Week 12
Project Presentation Slides | Talhah | bar: Week 11 to Week 12
Phase Presentation |  | Week 12: 4/10 (Thursday)
Implementation | bar: Week 12 to Week 15
Testing | bar: Week 12 to Week 15
Maintanence | bar: Week 12 to Week 15
Final Submission | bar: Week 15
Final Presentation | bar: Week 16